## Sheet1
User Story ID | User Story | Sprint # | Start | Finish | Priority | Estimate | Return on Investment | Status
|  | Sprint 1 | 27/1/2020 | 31/1/2020
14 | As a customer, I can access the home page |  | 27/1/2020 | 28/1/2020 | 10 | 3 | 3.3333 | Completed
1 | As a customer, I can search based on code |  | 27/1/2020 | 31/1/2020 | 10 | 4 | 2.5 | Completed
2 | As a customer, I can search based on procedure |  | 27/1/2020 | 31/1/2020 | 10 | 4 | 2.5 | Completed
3 | As a customer, I can search based on location |  | 27/1/2020 | 31/1/2020 | 9 | 9 | 1 | Completed
8 | As a customer, I can view search results in a list |  | 27/1/2020 | 31/1/2020 | 8 | 1 | 8 | Completed
9 | As a customer, I can view search results on a map |  | 27/1/2020 | 31/1/2020 | 8 | 7 | 1.1429 | Completed
12 | As a customer, I can view details of a search result in the list |  | 27/1/2020 | PUSHED TO SPRINT 2 | 7 | 2 | 3.5 | In-progress
4 | As a customer, I can sort search results based on price |  | 28/1/2020 | 31/1/2020 | 6 | 2 | 3 | Completed
6 | As a customer, I can sort search results based on location |  | 28/1/2020 | 31/1/2020 | 6 | 2 | 3 | Completed
13 | As a customer, I can view details of a search result on a map |  | 28/1/2020 | PUSHED TO SPRINT 2 | 5 | 7 | 0.71429 | In-progress
10 | As a customer, I can set a price range for my search |  | 27/1/2020 | 31/1/2020 | 4 | 1 | 4 | Completed
11 | As a customer, I can set a distance range for my search |  | 28/1/2020 | 31/1/2020 | 4 | 1 | 4 | Completed
16 | As a customer, I can view service provider information page |  | 27/1/2020 | 31/1/2020 | 4 | 3 | 1.3333 | Completed
7 | As a customer, I can sort search results based on "best match" |  | 28/1/2020 | PUSHED TO SPRINT 2 | 2 | 4 | 0.5 | Completed
User Story ID | User Story | Sprint # | Start | Finish | Priority | Estimate | Return on Investment | Status
|  | Sprint 2 | 2020-03-02 | 2020-07-02
12 | As a customer, I can view details of a search result in the list |  | 27/1/2020 |  | 7 | 2 | 3.5 | In-progress
13 | As a customer, I can view details of a search result on a map |  | 28/1/2020 |  | 5 | 7 | 0.71429 | In-progress
17 | As an admin, I can login to an admin account |  |  |  | 3 | 5 | 0.6 | Not Started
19 | As an admin, I can add a new medical centre |  |  |  | 3 | 7 | 0.42857 | Not Started
20 | As an admin, I can remove a medical centre |  |  |  | 3 | 7 | 0.42857 | Not Started
18 | As an admin, I can edit details of a medical centre |  |  |  | 3 | 8 | 0.375 | Not Started
7 | As a customer, I can sort search results based on "best match" |  | 28/1/2020 |  | 2 | 4 | 0.5 | In-progress
5 | As a customer, I can sort search results based on rating |  |  |  | 1 | 8 | 0.125 | Not Started
15 | As a customer, I can rate a medical centre |  |  |  | 1 | 8 | 0.125 | Not Started

## Sheet2 (hidden)
Not Started
In-progress
Completed