## Sprint 2
Backlog Task & ID | Priority | Lead for task | Also assigned | Status | Overall Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review | Date of addition
1. As a customer, I can search based on procedure | 10 |  |  | Completed | 9
Webpage link to API to call database search results |  | AN | AI | In-Progress | 9
Update design of search function |  |  |  | In-Progress | 3
Reseach and follow accessibility guidelines |  | AR |  | In-Progress | 3 | 2 | 0
3. As a customer, I can search based on location | 9 |  |  |  | 4
Finalise Live Location implementation |  | AI |  | Completed | 4 | 4 | 0
9. As a customer, I can view search results on a map | 8 |  |  |  | 8
Integrate Map functionality with front-end |  | WM |  | Completed | 5
Map displays information about provider |  | WM |  | In-Progress | 3 | 0 | 1
21. As a customer, I can click a search result in the list and view it on the map | 7 |  |  |  | 2
Map moves to location |  | AN | WM | Completed | 1 | 0 | 1
Map zooms appropriately |  | WM | AN | Completed | 1 | 0 | 1
10. As a customer, I can set a price range for my search using a slider | 4 |  |  |  | 4
Create slider for price range on search page |  | AN |  | Completed | 2 | 0 | 0
Pass variables from price slider to the results page |  |  |  |  | 2
11. As a customer, I can set a distance range for my search using a slider | 4 |  |  |  | 4
Create slider for distance range on search page |  | AG | AI | Completed | 2 | 2 | 0
Pass variables from distance slider to the results page |  |  |  |  | 2
16. As a customer, I can view service provider information page | 4
Update contact page design |  | AI |  | In-Progress | 4 | 4 | 3
Send a query by email implementation |  | AI |  | In-Progress | 4 | 4 | 2
17. As an admin, I can login to an admin account | 3 |  |  |  | 5
19. As an admin, I can add a new medical centre | 3 |  |  |  | 7
20. As an admin, I can remove a medical centre | 3 |  |  |  | 7
18. As an admin, I can edit details of a medical centre | 3 |  |  |  | 8
7. As a customer, I can sort search results based on "best match" | 2 |  |  |  | 4
5. As a customer, I can sort search results based on rating | 1 |  |  |  | 8
15. As a customer, I can rate a medical centre | 1 |  |  |  | 8
Total
Team Members unit of work
Andrius (AN) -
Alek (AR) -
Amy (AG) -
Aylin (AI) -
William (WM) -
Calum (CW) -

## Sheet2
Not Started
In-Progress
Completed

## Sheet1 (hidden)
Not Started
In-Progress
Completed