## Sprint 1
Backlog Task & ID | Priority | Assigned to | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
14. As a customer, I can access the home page | 10
Design the theme and layout for the website |  | AI, WM, AG | Completed | 2 | 0 | 0
Implement the design |  | AI, WM, AG | Completed | 4 | 2 | 0
1. As a customer, I can search based on code | 10
Create search bar on webpage allowing user input |  | AI, WM, AG | Completed | 1 | 0 | 0
Webpage link to API to call database search results |  |  | Not Started | 2 | 2 | 2
Search functionality in database |  | AN | Completed | 3 | 1 | 0
2. As a customer, I can search based on procedure | 10
Create search bar on webpage allowing user input |  | AI, WM, AG | Completed | 1 | 0 | 0
Webpage link to API to call database search results |  |  | Not Started | 2 | 2 | 2
Search functionality in database |  | AN | Completed | 3 | 1 | 0
3. As a customer, I can search based on location | 9
Create multiple search bars on webpage allowing user input |  | AG, AI | In-Progress | 2 | 1 | 1
Access the device's co-ordinates to enable a LIVE Location search |  | WM, AI, AR | In-Progress | 5 | 5 | 2
Webpage link to API to call database search results |  |  | Not Started | 2 | 2 | 2
Assign co-ordinates to all providers in the database |  | AR | In-Progress | 5 | 3 | 3
Search functionality in database |  | AN | Completed | 8 | 8 | 0
8. As a customer, I can view search results in a list | 8
Create results page for website to return list |  | AG, AI | In-Progress | 4 | 3 | 2
Webpage link to API to call database search results |  |  | Not Started | 2 | 2 | 2
Return list from database in order of provider ID |  | AN | Completed | 3 | 0 | 0
9. As a customer, I can view search results on a map | 8
Research map API functionality |  | AR, WM,AI | Completed | 4 | 3 | 0
Webpage link to API to call database search results |  |  | Not Started | 2 | 2 | 2
Return list from database from nearest to location |  | AN | Completed | 8 | 8 | 0
12. As a customer, I can view details of a search result in the list | 7
Access a further details page on a specific search result (button call) |  |  | Not Started | 2 | 2 | 2
Return full set of details on a specific provider ID from DB |  | AN | Completed | 2 | 0 | 0
4. As a customer, I can sort search results based on price | 6
Sort by button option on UI (API call) |  |  | In-Progress | 3 | 3 | 2
Return list from database in order of price |  | AN | In-Progress | 2 | 2 | 2
6. As a customer, I can sort search results based on location | 6
Sort by location button on UI (API call) |  |  | In-Progress | 3 | 3 | 2
Return list from database in order of distance from address |  | AN | In-Progress | 2 | 2 | 2
13. As a customer, I can view details of a search result on a map | 5
Access a further details page on a specific search result (button call) |  |  | Not Started | 2 | 2 | 2
Return full set of details on a specific provider ID from DB |  | AN | In-Progress | 1 | 1 | 1
10. As a customer, I can set a price range for my search | 4
Price range option on UI |  | AI, AG | Completed | 1 | 0.5 | 0
Webpage link to API to call database search results |  |  | Not Started | 2 | 2 | 2
Return list from database between a price range |  | AN | Completed | 2 | 0 | 0
11. As a customer, I can set a distance range for my search | 4
Distance range option on UI |  | AI, AG | Completed | 1 | 1 | 0
Webpage link to API to call database search results |  |  | Not Started | 2 | 2 | 2
Return list from database between a distance range |  | AN | Completed | 2 | 2 | 0
16. As a customer, I can view service provider information page | 4
Design CraneWare contact page |  | AG | Completed | 1 | 0 | 0
Implement the design |  | AG | In-Progress | 2 | 1 | 1
7. As a customer, I can sort search results based on "best match" | 2
Sort by 'best match' option on UI |  |  | Completed | 1 | 1 | 0
Create formula for determining 'best match' |  | CW, AR | In-Progress | 3 | 3 | 2
Sort by 'best match' functionality |  |  | Not Started | 2 | 2 | 2
Total |  |  |  | 99 | 74.5 | 40 | 0 | 0 | 0

## Sheet1 (hidden)
Not Started
In-Progress
Completed

## Sprint 2
Backlog task & ID | Story points | Assigned to | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
User Story #
User Story #
User Story #
User Story #
User Story #
User Story #